## Cost Estimate
Grant Application Cost Estimate Template
* NTA templates are locked - In certain circumstances if the templates are to be unlocked for editing (additional lines etc… (no deleting allowed) - the request is to be put in writing to the NTA Programme Manager for approval
NOTE: the activity cost heads presented are indicative for a linear project, if the project being reported (undertaken/developed) is not a linear project, activity cost heads are to be discussed and agreed in writing with NTA prior to the production of the cost estimate. | [9 empty] | Guidance Notes | * All cells in purple - input is required | ** Figures (€) are only illustrative ****
Project Title: |  |  | ************ | [6 empty] | Sponsoring Agency (SA) to list out the project title
Project / Contract Code: |  |  | DLR/22/0015G | Prepared By (Individual & Organisation) |  |  | Sally Gate - South Dublin Council |  |  | SA confirm the project code
Approving Authority: |  |  | NTA | Date Estimate Prepared: |  |  | 2022-07-09 |  |  | Approving authority is always NTA: Date application is submitted
Sponsoring Agency: |  |  | South Dublin Council | Base Date of Estimate: |  |  | Q3 2022 |  |  | SA = local authority (or Irish Rail / Bus Éireann etc ...) submitting the application: Base date is the quarter period (Q1 = Jan / Feb / march: Q2 = Apr / May / June: Q3 = July / Aug / Sept: Q4 = Oct / Nov / Dec)
Project Information | [8 empty] | 1
2
Mainline Cross-Section Type: |  |  | Local Road | Location: |  | ****** |  |  | 3 | Identify location - include co-ordinates if available
4
Total Mainline Length (m): |  |  | 500 | Traffic Impact Rating (DCC Only): |  |  |  |  | 5 | SA to confirm the total length of construction: List impact rating on scale 1 to 5 (5 been the highest - click the cell for dropdown if applicable) - leave blank if N/A
Total Mainline Width (m): |  |  | 2 | Land take Required:
Potential Construction Works Start Date: |  |  | Q1 2023 | Anticipated Construction Period: |  | 2 | Months |  |  | SA to confirm potential start on site (Quarter): SA to confirm estimated construction period
Other Relevant Project Information: |  |  | New Footpath & Public Lighting | [6 empty] | SA to outline (brief) project scope of works
1 | Grant Application Cost Estimate
| Ref | Description |  | Quantity | Unit | Rate | Total (€)
| 1.1 | Construction Costs |  | 0.5 | Km | 400000 | 200000 |  | Item | If backup is available - use the Calculation sheet tab - If no back-up give explanation to costing source as per excel line B62 below
| Sub-Total A - Construction Costs | [5 empty] | 200000 |  | Km
| Add-On Costs | [7 empty] | M
| 1.2 | Preparation and Administration Costs |  |  |  |  | 60000 |  | Nr | SA to confirm admin costs (design teams etc …)
| 1.2.1 | Scope & Purpose |  | 1 | Item | 7500 | 7500
| 1.2.2 | Concept, Development & Option Selection |  | 1 | Item | 11000 | 11000
| 1.2.3 | Preliminary Design |  | 1 | Item | 5000 | 5000
| 1.2.4 | Statutory Processes |  | 1 | Item | 5000 | 5000
| 1.2.5 | Detailed Design & Procurement |  | 1 | Item | 14000 | 14000
| 1.2.6 | Construction & Implementation |  | 1 | Item | 15000 | 15000
| 1.2.7 | Close Out & Review |  | 1 | Item | 2500 | 2500
| 1.3 | Traffic Management (TM) Related Costs |  | 10% | % | 200000 | 20000 |  | M2 | SA to allow costs (estimate) for TM (if applicable to there project)
| 1.4 | Land and Property Costs (inclusive of inflation) |  | 1 | Item | 67500 | 67500 |  |  | SA to estimate the costs - confirm in assumptions tab the m2 take and the estimated rate
| Sub-Total B - Add-ons | [5 empty] | 147500
Adjustments
| 1.5 | Inflation (Band 2 & 3 Projects Only) |  |  | % | 280000 | 0 |  | % | Note, no entry required for Band 1 projects
| 1.6 | Add Contingency Allowance (001_B123_CC_CMG) |  | 30% | % | 280000 | 84000 |  | Item | SA to confirm - refer to contingency calculator (form 001) - 30% is as per the worked example (note, contingency allownce should always be included)
| 1.7 | Per Cent for Art Scheme https://publicart.ie/main/commissioning/funding/per-cent-for-art-scheme/ |  | 1% | % | 280000 | 2800 |  |  | SA to review web link for proposed maximum limits. Figure to be reduced in cell J47 if required.
| Sub-Total C - Adjustments | [5 empty] | 86800
| Total Grant Application Cost Estimate (excluding VAT) | [5 empty] | 434300
| VAT on Construction and TM Costs (including Contingency & Inflation) |  |  | 13.5% | % | 306800 | 41418 |  |  | 13.5% VAT is applied to the construction estimate / traffic management / inflation allowance / contingency allowance / Arts
| VAT on Preparation & Administration Costs |  |  | 23% | % | 60000 | 13800 |  |  | 23% applies to preparation costs (design teams as an example): No VAT should be applied if design is in-house with the SA
| VAT on Land and Property |  |  | 1 | Item
| https://www.revenue.ie/en/vat/vat-on-property-and-construction/vat-and-the-supply-of-property/index.aspx | [8 empty] | SA to note - certain VAT rules apply to land take - refer to the link in line C54 to determine if VAT is applicable to your project
| Total Grant Application Cost Estimate (Including VAT) | [5 empty] | 489518
| Mainline Length |  | 0.5 | Km |  | Rate Per Km (Excluding VAT) | 868600 |  |  | SA to insert mainline length = this will automatically confirm the € / KM
[6 empty] | Rate Per Km (Including VAT) | 979036
Source of Cost Data (Please provide a brief narrative on the source of cost data in the box below)
| Cost estimate is based on works of similar nature where we have a contractor on site. Additionally, we also have a cost from a utility supplier for the public lighting works. It will be the South Dublin Council's proposal to use a contractor (framework) to carry out the works based on tender returns (MEAT) | [8 empty] | SA to confirm where costs have dererived from (example, similar works on site with contractor price per m applied to the current cost estimate). Refer to the Calculation tab if there is a breakdown available (example, if quantities known, apply QTY x Rates: Or if works are direct labour, identify the labour costs & material costs (note, no VAT to be applied on labour if direct labour by the SA)
2 | Risk
| Please include details of known key project risks. (Additional rows to be added as required) Please rank risks in order of severity with 5 being most severe. |  |  | Risk |  |  |  | Rank |  | SA to list possible risks as noted
(no Risk Register (form 004) is required at this phase)
Revision | Title |  |  | Prepared By | Checked By |  | Issue Date
|  |  |  | Sally Gates | Michael Bunny |  | 2022-07-09 |  |  | SA to sign off (2 parties within their organisation)
NOTE: | Costs are reflective of costs at the base date stated above. Costs are considered include allowances for overheads and profit. VAT is not applicable to all land and property therefore it is not appropriate to apply a uniform percentage. The value associated with VAT on land and property is to be determined on an individual basis and included as a lump sum.
Check Box If Yes
Note on J14: Estimating Methodology Period in which prices in the cost estimate relate to (e.g. Q1 2021)
Note on I52: Estimating Methodology: VAT Rates shall be reviewed to ensure that they are correct and are being applied to the correct cost heads.
Note on I53: Estimating Methodology: VAT Rates shall be reviewed to ensure that they are correct and are being applied to the correct cost heads.
Note on I54: Estimating Methodology The applicable VAT rate is to be determined by each user individually. A hyperlink to applicable rules/laws relating to the applicability of VAT is included for reference and assessment purposes.

## Assumptions
Estimate Assumptions, Exclusions and Inclusions
[7 empty] | Guidance Notes | * All cells in purple - input is required
| Project Title: |  | ************ |  |  |  | No action required - the text is carried forward automatically from the Cost Estimate tab
| Project / Contract Code: |  | DLR/22/0015G |  |  |  | No action required - the text is carried forward automatically from the Cost Estimate tab
| Approving Authority: |  | NTA |  |  |  | No action required - the text is carried forward automatically from the Cost Estimate tab
| Sponsoring Agency: |  | South Dublin Council |  |  |  | No action required - the text is carried forward automatically from the Cost Estimate tab
| Prepared By (Individual/Organisation): |  | Sally Gate - South Dublin Council |  |  |  | No action required - the text is carried forward automatically from the Cost Estimate tab
| 1 | Construction Costs
We have quantities confirmed and have applied rates to the quantities based on works of similar nature and made allowances for 'today's costs'. We also have a quote on the Public lighting which will be part of the main contractors works package
SA to give as much information as possible
(if works were to be done by direct labour - the SA should advise the NTA to refer to the calculation sheet for the backup to the cost estimate)
Potential Start Date:
| 2 | Delivery and Construction Programme
SA to give programme information as per dates in Cost Estimate tab
| 3 | Preparation and Administration Costs
|  | Any assumptions, exclusions or inclusions that have been made in relation to preparation and administration (design & supervision) shall be clearly identified in this section. Substantiation/justification of the percentage applied in the cost estimate shall be provided in this section. |  |  |  |  | SA to include costs for design / administration costs
(example purposes - the cost estimate includes for design team / consultant)
| 4 | Traffic Management Related Costs
We have inlcuded traffic management costs so as to expediate works on site and also eliminate risks (traffic accidents)
SA to confirm if traffic management (TM) is included or not (not required) - If TM was not required, state TM is not required on site
| 5 | Land and Property Costs
|  | We confirm there is 45m2 of land take required. We estimate the cost to be €1,500 per m2 to include any remedial works on the land take. We are in discussion with the effected parties and no main concerns to report. |  |  |  |  | SA to give information on estimated costs / quantity if land take (m2) / negotiations if any that have occurred / flag any issues
| 6 | Other Relevant Information |  |  |  |  | SA to provide if any additional information is required to be completed
Any other relevant information, general assumptions, exclusions or inclusions that have been used to develop the cost estimate shall be included in this section.
| Revision | Title |  | Prepared By | Checked By | Issue Date
|  |  |  | Sally Gates | Michael Bunny | 2022-07-09 | SA to sign off (2 parties within their organisation)

## Grant Application Summary
Grant Application Cost Estimate Summary
NOTE: The information below will be auto-generated from the main cost estimate template to obtain the relevant totals in line with the seven costs heads required for inclusion within the grant application form. | [9 empty] | Guidance Notes
Project Title: |  |  | ************ | [6 empty] | No action required - the text is carried forward automatically from the Cost Estimate tab
Project / Contract Code: |  |  | DLR/22/0015G | Prepared By (Individual & Organisation) |  |  |  |  | Sally Gate - South Dublin Council | No action required - the text is carried forward automatically from the Cost Estimate tab
Approving Authority: |  |  | NTA | Date Estimate Prepared: |  |  |  |  | 2022-07-09 | No action required - the text is carried forward automatically from the Cost Estimate tab
Sponsoring Agency: |  |  | South Dublin Council | Base Date of Estimate: |  |  |  |  | Q3 2022 | No action required - the text is carried forward automatically from the Cost Estimate tab
1 | Grant Application Cost Estimate - Summary |  |  |  |  | Sub-Total | VAT % | VAT Amount | Total Incl. VAT
| 1.2.1 | Scope & Purpose |  | 1 | Item | 7500 | 23 | 1725 | 9225 | No action required - the text is carried forward automatically from the Cost Estimate tab
| 1.2.2 | Concept, Development & Option Selection |  | 1 | Item | 11000 | 23 | 2530 | 13530 | No action required - the text is carried forward automatically from the Cost Estimate tab
| 1.2.3 | Preliminary Design |  | 1 | Item | 5000 | 23 | 1150 | 6150 | No action required - the text is carried forward automatically from the Cost Estimate tab
| 1.2.4 | Statutory Processes |  | 1 | Item | 5000 | 23 | 1150 | 6150 | No action required - the text is carried forward automatically from the Cost Estimate tab
| 1.2.5 | Detailed Design & Procurement |  | 1 | Item | 14000 | 23 | 3220 | 17220 | No action required - the text is carried forward automatically from the Cost Estimate tab
| 1.2.6 | Construction & Implementation |  | 1 | Item | 15000 | 23 | 3450 | 18450 | No action required - the text is carried forward automatically from the Cost Estimate tab
| 1.2.7 | Close Out & Review |  | 1 | Item | 2500 | 23 | 575 | 3075 | No action required - the text is carried forward automatically from the Cost Estimate tab
| 1.2.8 | Traffic Management |  | 1 | Item | 20000 | 13.5 | 2700 | 22700
| 1.2.9 | Land & Property Costs |  | 1 | Item | 67500 |  |  | 67500
| 1.2.10 | Construction Costs (Main Contractor) |  | 1 | Item | 200000 | 13.5 | 27000 | 227000 | No action required - the text is carried forward automatically from the Cost Estimate tab
| 1.2.11 | Inflation Allowance (Band 2/3 Only) |  | 1 | Item | 0 | 13.5 | 0 | 0
| 1.2.12 | Contingency Allowance |  | 1 | Item | 84000 | 13.5 | 11340 | 95340 | No action required - the text is carried forward automatically from the Cost Estimate tab
| 1.2.13 | Allowance for Arts (%) |  | 1 | Item | 2800 | 13.5 | 378 | 3178 | No action required - the text is carried forward automatically from the Cost Estimate tab
|  |  |  | Sub-Total (Ex.VAT) |  | 434300
| Add VAT on Land (If Applicable) | [7 empty] | 0 | No action required - the text is carried forward automatically from the Cost Estimate tab
| Total Grant Application Cost Estimate (Including VAT) | [7 empty] | 489518 | No action required - tot's automatically
NOTE: | Costs are reflective of costs at the base date stated above. Costs are considered to include allowances for overheads and profit.
Note on L14: Estimating Methodology Period in which prices in the cost estimate relate to (e.g. Q1 2021)

## Expenditure Profile
Expenditure Profile
|  |  |  | Guidance Notes | * All cells in purple - input is required
Project Title: |  | ************ |  | No action required - the text is carried forward automatically from the Cost Estimate tab
Project / Contract Code: |  | DLR/22/0015G |  | No action required - the text is carried forward automatically from the Cost Estimate tab
Total Preliminary Cost Estimate: |  | 489518 |  | No action required - the text is carried forward automatically from the Cost Estimate tab - Include figure with VAT
Anticipated Programme Duration: |  | 2 | Months | No action required - the text is carried forward automatically from the Cost Estimate tab
Grant Application Cost Estimate
Year | Quarter | Total Quarterly Expenditure (€) | Total Cumulative Expenditure (€)
Year 1 | Q1 |  | 0
| Q2 |  | 0
| Q3 |  | 0
| Q4 |  | 0
Year 2 | Q1 | 489518 | 489518 | SA to include the expenditure per quarter - note in the worked example the estimated programme is 2 months with a start date is Q1 2023 so the full expenditure applies
| Q2 |  | 489518
| Q3 |  | 489518
| Q4 |  | 489518
Year 3 | Q1 |  | 489518
| Q2 |  | 489518
| Q3 |  | 489518
| Q4 |  | 489518
Year 4 | Q1 |  | 489518
| Q2 |  | 489518
| Q3 |  | 489518
| Q4 |  | 489518
Revision | Title
Note:
Years and quarters stated are for illustrative purposes only. Please amend to suit the project duration. Expenditure Profile must be demonstrated quarterly unless otherwise agreed with NTA.

## Calculation Sheet
Guidance Notes (If works carried out by direct labour - Example below)
Ref | Description | QTY | Unit | Rate | Total | ** Figures are only illustrative ****
| Labour |  |  |  |  | No VAT (13.5%) to be applied on SA direct labour costs
| - Supervisor (2 months) | 40 | day | 250 | 10000
| - General operative - 5 number (2 months) | 200 | day | 170 | 34000
| - Carpenter 2 number (1 months) | 40 | day | 200 | 8000
52000
Specialist Contractor (******** Utilities Limited)
| Public Lighting Works: -Supply & Installation of * No. 8m Octagonal Public Lighting Columns -Supply & Installation of * No. Fuse Units -Supply & Installation of * No. Urbis Axia LED Lanterns -Supply & Installation of * No. Photocell Units -Supply & Install * No. Unmetered Micro Pillar -* No. ESB Unmetered Connection Fees and Applications Complete -Supply & Install of PL Cable & Accessories as required -Testing and Commissioning included | 1 | item | 35000 | 35000
[5 empty] | 35000 | SA to include for VAT (13.5%) on specialist works contractor
| Materials |  |  |  |  | SA to include VAT on materials at 23%
| - Concrete | 200 | m3 | 135 | 27000
| - SR21 stone | 1500 | m3 | 25 | 37500
| - Timber 100 x 50mm (110 no 4.8m lengths) | 115 | no | 18 | 2070
| - Mesh A142 - 110 sheets | 110 | no | 50 | 5500
| - Kerbs | 560 | no | 20 | 11200
| - Lean mix | 50 | m3 | 120 | 6000
| - Nails | 1 | item | 3500 | 3500
| - Spray paint | 1 | item | 150 | 150
| - Ancillary hire tools | 1 | item | 4000 | 4000
| - PPE for staff (including signage) | 1 | item | 3500 | 3500
| - Portaloo hire for 2 months | 8 | weeks | 200 | 1600
102020
|  |  |  | 23% | 23464.6
125484.6